## Sheet1
Task | Start | End | Duration/ Days | Status
Sensor selection and calibration | 27/01/2026 | 29/01/2026 | 2 | Completed
Microcontroller setup and sensor interfacing | 29/01/2026 | 30/01/2026 | 1 | Completed
Display module integration and UI design | 30/01/2026 | 31/01/2026 | 1 | Completed
Data logging implementation | 2026-01-02 | 2026-01-02 | 0 | Completed
System validation and error compensation | 2026-02-02 | 2026-03-02 | 1 | Completed
Optional alert mechanism | 2026-03-02 | 2026-04-02 | 1 | Completed